## Instructions
The TCS Learning Collaborative Milestones Map helps MCPs understand TCS policy expectations, assess their current readiness using the EPIS phases, and track progress at key checkpoints. It also guides MCPs in selecting priority areas that need focused improvement to ensure consistent and effective implementation of TCS requirements.
Instructions
Step 1 | Step 2 | Step 3 | Step 4
In cell A1 enter your MCP name Review TCS Policy Requirements (Columns A and B). Policy Requirements reflect the core TCS policy expectations that every MCP must meet, regardless of internal workflow or structure. The core policy requirements consist of policy domains and policy elements. Policy domains are the major categories of the requirements within the TCS policy. Policy elements specify the required actions that make up the TCS policy domains. | Review Illustrative Inputs and Measurements (Columns C and D) and make edits as needed. The Illustrative Inputs & Measurements are optional examples intended to help MCPs think through what resources and metrics might support each Policy Element. They are not required and may be adapted or replaced based on your MCP’s structure, data systems, contracting model, and existing processes. As you analyze them, consider whether each example reflects what you already do, highlights a gap, or points to an area that may need further development. They are simply starting points to help you evaluate your existing capacity and identify opportunities for improvement. | At each checkpoint in the Learning Collaborative (Columns E, F, G), you will select the EPIS phase from the dropdown that best reflects your MCP’s progress on each Policy Element. Choose Exploration if you are still assessing needs, understanding gaps, or determining how the requirement fits into your system. Choose Preparation if you are planning and building readiness, such as developing workflows, roles, or partnerships. Choose Implementation when the requirement is actively being put into practice. Choose Sustainment when the requirement is functioning reliably and embedded in routine operations. For additional detail on these phases, refer to https://episframework.com/what-is-epis. | In Column Choose H, select three Priority Areas that represent the TCS policy elements and implementation needing the most attention, improvement, or development for your MCP. These selections will help focus your MCP’s effort and guide progress tracking throughout the Learning Collaborative. For each chosen Priority Area, provide a brief description of your current implementation status and note the progress you expect to achieve by July 2026 in Column I.

## TCS Policy Implementation
MCP Name:
Policy Requirements |  | Illustrative Inputs and Measurements |  | Implementation Checkpoints |  |  | Priority Areas
Policy Requirements reflect the core expectations outlined in the TCS policy. They describe what every MCP must have in place to meet statewide TCS obligations, regardless of internal structure, workflows, or delivery models. These Requirements set the overarching standards that guide all subsequent policy details. |  | Illustrative Inputs and Measurements are examples only. MCPs may adapt or replace them based on their own workflows, data systems, and contracting models. Use these as a starting point to assess what you already have in place and what may need development. Measurements are suggested ways to monitor but will not be required reporting to DHCS. |  | Pre-Collaborative (March 2026) | Midpoint (June 2026) | Post Collaborative (September 2026) | Priority Area: A key part of TCS implementation that your MCP chooses to focus on because it needs the most attention, improvement, or development. These areas guide where you will concentrate effort and track progress during the Learning Collaborative.
Policy Domains | Policy Elements | Inputs - What is needed to complete the policy requirements? | Measurements - How do we track that the requirements are met? | What is the current status of the Policy Element? Select from the dropdown options below. Exploration - Evaluate needs & program fit Preparation - Plan how to integrate into system Implementation - Put the program into place Sustainment - Program is embedded For a more detailed description of each phase, please refer to: https://episframework.com/what-is-epis |  |  | Select 3 Priority Areas | If selected as a Priority Area, Provide a brief description of the current implementation status and the progress you expect to make by September 2026. | Tab with summary notes on progress for each session CMQCC to give analysis/summary each time this is filled out
Identification of TCS Category and Initiation of TCS Support | TCS Services begin at identification of pregnancy and no later than beginning of the 3rd trimester | 1. Identification of claim of initial comprehensive prenatal visit 2. Provider reporting of new prenatal patients 3. HIE download of new prenatal patients to a practice | # of pregnant women identified (monthly), with gestational age at the time of identification (average) |  |  |  | FALSE |  | goal to get everyone out of the explore phase
| Stratification of members to moderate intensity and high intensity | 1. Algorithm for high and moderate intensity criteria in place 1a. Birthing RSST high-risk 1b. OCI integration | % of PG/PP members identified as high-intensity and moderate-intensity % of PG/PP members identified as high-risk by RSST, OCI, etc. % PG/PP members with known TCS category |  |  |  | FALSE
| Identification of non-delivery hospital admissions for high intensity identification | 1. Data Exchange Agreements set up with participating facilities to receive ADT notifications 2. Oversight of facility discharge planning process in place | # of pregnant women admitted with non-delivery admissions |  |  |  | FALSE
| Ongoing re-evaluation of intensity assignment | Workflow for re-defining TCS category assessment conducted: upon pregnancy identification, changes in risk/status, at specific gestational age, delivery, update in RSST tier | % of pregnant members who change risk category throughout pregnancy/postpartum |  |  |  | FALSE
Identification of TCS Care Manager (High-intensity) | TCS Care Manager assigned as single point of contact | 1. Identification of staff who conduct care coordination and warm hand-offs 2. Workflow to assign ECM and CCM care manager as the same POC for TCS | # and/or % of members with ECM/CCM/other Care Managers |  |  |  | FALSE
| Primary maternity care site informed of POC (TCS Care Manager) | 1. Communication workflow with perinatal facility |  |  |  |  | FALSE
Identification of TCS Care Coordination (Moderate-intensity) | Identification of the care coordination entity (note: MCP can continue to fulfill care coordination responsibilities if there is no sufficient care coordination entity.) | 1. Contracting agreements in place or MCP assigns internal POC | # or % of members receiving care from a contracted entity |  |  |  | FALSE
| Notification of the care coordination entity that member meets moderate-intensity stratification. | 1. Communication workflow with perinatal facility
Establishment and operationalization of TCS Care Manager Responsibilities (high-intensity) | Discharge documentation review (discharge summary / discharge instructions), and facility coordination as needed | 1. Data Exchange Framework in place with Discharging Facilities |  |  |  |  | FALSE
| Post-discharge or post-pregnancy outreach with successful coordination within 7 days | 1. Coordination mechanisms in place | % of PG/PP members with contact within 7-days post-discharge |  |  |  | FALSE
| Follow-up care coordination | 1. Coordination mechanisms in place |  |  |  |  | FALSE
Establishment and operationalization of TCS Care Manager Responsibilities (moderate-intensity) | Discharge documentation review (discharge summary / discharge instructions) | 1. Oversight mechanism in place |  |  |  |  | FALSE
| Post-discharge or post-pregnancy outreach with successful connection within 21 days | 1. Coordination mechanisms in place | % of PG/PP members with contact within 21-days post-discharge |  |  |  | FALSE
| Dedicated team/phone number for member contact and support | 1. Escalation pathway in place |  |  |  |  | FALSE
Completion of Birthing Supports Checklist (BSC) | Referrals and warm handoffs to meet BSC needs | 1. Referral/handoff procedure established 2. Regularly updated referral list 3. Identification of licensed professionals to complete items as needed | # of completed referrals |  |  |  | FALSE
| MCPs responsible for ensuring completion | Communication workflow with TCS care manager or care coordination entity to ensure BSC is updated at defined checkpoints. |  |  |  |  | FALSE
| Completion continues throughout pregnancy | 1. Integration into existing workflows and/or EHR |  |  |  |  | FALSE
Completion of High-Intensity TCS (Support ends when all needs are met, minimum 60 days from end of pregnancy, and/or 30 days after discharge) | Completion of postpartum medical visit | 1. Communication workflow with primary maternity care facility | % of postpartum visits completed as appropriate |  |  |  | FALSE
| Completion of 2 month well-child visit | 1. Communication workflow with pediatric or primary care facility | % of 2-month WCVs completed |  |  |  | FALSE
| Completion of follow up in discharge instructions | [5 empty] | FALSE
Completion of Moderate-Intensity TCS (Support ends when all needs are met, minimum of 60 days following end of pregnancy) | Completion of postpartum medical visit | 1. Communication workflow with primary maternity care facility | % of postpartum visits completed as appropriate |  |  |  | FALSE
| Completion of 2 month well-child visit | 1. Communication workflow with pediatric or primary care facility | % of 2-month WCVs completed |  |  |  | FALSE
| Completion of follow up in discharge instructions | [5 empty] | FALSE